## Slide 1
Completing the KMS
14 steps to a REST-fronted key management service
Design impact · proposed solution · test strategy, for every step
14
steps in 5 stages
50
features short of full coverage
34
closed by this plan
16
deferred, with reasons
Baseline e44a2ef · 816 tests green · 11 September 2026
Notes: Three slides per step: what it does to the existing design, what gets built, and how it is proven. Every word in this deck comes from plan_steps.json, which the plan generator emits — the deck cannot say anything the written plan does not.

## Slide 2
THE PLAN AT A GLANCE
5 stages, 14 steps
A · Foundation
No new attack surface. Makes the rest safe to build.
1
Service layer and guard
—
2
Query and reporting layer
+2
B · The REST control plane
The API, then the console that uses it.
3
HTTP transport, sessions and service accounts
+3
4
Read endpoints
—
5
Write endpoints, and the governance gaps
+4
6
Administration, OpenAPI, separation of duties
+3
7
Web console and self-service
+2
C · Enterprise fit
What an auditor and a security team ask for.
8
Enterprise identity and policy
+2
9
Audit externalisation, compliance and ceremony
+7
D · Scale, availability and tenancy
Needs infrastructure to verify.
10
Storage abstraction and PostgreSQL
+1
11
High availability, failover and deployment
+6
12
Multi-tenancy
+2
E · Protocol and estate reach
Additive, independent of D, verifiable here.
13
KMIP JSON and XML encodings
+1
14
Certificate discovery and expiry monitoring
+1
+n is the number of gap-matrix features the step closes. Steps 1 and 2 close nothing and are the two the rest depends on.
Notes: Order is dictated by dependency. Step 1 must precede everything: authorization, dual control and audit currently live inside the KMIP dispatcher, and a REST layer built before they move would bypass all three silently.

## Slide 3
STEP 1 OF 14 · DESIGN IMPACT
Service layer and guard
Make authorization, dual control, audit and metrics impossible to bypass — before a second transport exists to bypass them.
Stage A
WHAT CHANGES IN THE EXISTING DESIGN
OperationDispatcher loses its cross-cutting logic and becomes a codec: decode, call the service, encode.
access_control.py and dual_control.py are invoked from one place instead of being wired into a transport.
No schema change, no configuration change, nothing on the wire changes.
THE SHAPE OF THE SOLUTION
A new kmip_pkcs11/service/ package: CallContext (identity, peer address, transport), a guard() context manager, and KeyService / AdminService facades over the existing handlers and store.
The guard runs the role allowlist, then dual control, then the operation, then audit and metrics — the exact order dispatch() uses today.
OperationDispatcher shrinks to: decode TTLV, call the service, encode TTLV.
Notes: Objective: Make authorization, dual control, audit and metrics impossible to bypass — before a second transport exists to bypass them.

## Slide 4
STEP 1 OF 14 · PROPOSED SOLUTION
Service layer and guard
Make authorization, dual control, audit and metrics impossible to bypass — before a second transport exists to bypass them.
Stage A
WHAT GETS BUILT
Move check_operation_allowed, dual_control_enforce, _audit and _record_metric out of the dispatcher into the guard. Operation handlers are not touched.
Every service method takes a CallContext as its first argument, so a caller cannot forget to say who is asking.
Closes no gap-matrix feature directly. It exists so that every step after it can be built without re-litigating authorization — and so a later endpoint cannot silently become a path around dual control.
Estimated size: ~600 lines moved, ~15 new tests. No new dependencies.
Notes: Objective: Make authorization, dual control, audit and metrics impossible to bypass — before a second transport exists to bypass them.

## Slide 5
STEP 1 OF 14 · TEST STRATEGY
Service layer and guard
Make authorization, dual control, audit and metrics impossible to bypass — before a second transport exists to bypass them.
Stage A
WHAT THE TESTS HAVE TO PROVE
The existing suite must pass unmodified — this step changes no behaviour, and a test that needed editing would mean it did.
New: a reflection test that enumerates every public method on the service classes and asserts each one is guard-wrapped. This is the test that stops step 5 from quietly reintroducing a bypass.
New: guard writes an audit row on success and on failure; consumes a dual-control approval before the handler runs, not after; records metrics on both paths.
GATE
All 816 existing tests pass with no test file modified, and the reflection test proves no service method escapes the guard.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 6
STEP 2 OF 14 · DESIGN IMPACT
Query and reporting layer
Let the store answer the questions a console asks, in one query rather than N+1.
Stage A
WHAT CHANGES IN THE EXISTING DESIGN
metadata/store.py gains paged query methods; the existing locate() is untouched, so the KMIP handler is unaffected.
New indexes on the sortable columns — the first schema migration since Phase 1.
THE SHAPE OF THE SOLUTION
store.locate_page(filters, sort, cursor, limit) returning full rows, an opaque cursor and a total — not the bare identifiers Locate returns.
Cursor is (sort key, uid) encoded, not an offset: offset paging over a table that is being written double-shows rows.
store.inventory_report() and store.algorithm_usage() for the two reporting gaps.
Notes: Objective: Let the store answer the questions a console asks, in one query rather than N+1.

## Slide 7
STEP 2 OF 14 · PROPOSED SOLUTION
Query and reporting layer
Let the store answer the questions a console asks, in one query rather than N+1.
Stage A
WHAT GETS BUILT
Add the new methods beside the existing locate(), which stays exactly as it is for the KMIP handler.
Indexes to match the sort columns the console offers.
CLOSES 2 GAP-MATRIX FEATURES
Key inventory and discovery
Crypto-agility reporting
Estimated size: ~400 lines, ~20 tests.
Notes: Objective: Let the store answer the questions a console asks, in one query rather than N+1.

## Slide 8
STEP 2 OF 14 · TEST STRATEGY
Query and reporting layer
Let the store answer the questions a console asks, in one query rather than N+1.
Stage A
WHAT THE TESTS HAVE TO PROVE
Paging over a table mutated between pages neither duplicates nor skips a row — insert and delete between fetches and assert the union.
Sort by each supported column, ascending and descending; total equals a brute-force count; a tampered cursor is rejected rather than trusted.
Inventory and algorithm counts match a brute-force scan of the same store.
GATE
A store holding 12,000 objects returns page one of fifty, sorted by expiry, in a single query, with the same figures a full scan produces.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 9
STEP 3 OF 14 · DESIGN IMPACT
HTTP transport, sessions and service accounts
An authenticated HTTPS listener that shares nothing with the KMIP port, and cannot be flooded.
Stage B
WHAT CHANGES IN THE EXISTING DESIGN
A second listener and a second authenticated entry point: the security surface roughly doubles.
New config section, new tables for tokens, new failure modes the KMIP path never had (429, CSRF).
observability.py keeps its own unauthenticated port, deliberately separate.
THE SHAPE OF THE SOLUTION
New api: configuration section — own port, TLS mandatory, off by default. Not the observability port: /metrics and /ready are deliberately unauthenticated and must stay that way.
Opaque 256-bit tokens stored as SHA-256 hashes, with identity, label, created / expires / last used / revoked. Not JWTs: revocation matters more than statelessness, and there is already a database.
Browsers get an httpOnly, Secure, SameSite cookie plus a CSRF token; machine clients send a bearer header. Long-lived labelled tokens are the service-account mechanism.
A bounded connection semaphore and a per-identity token bucket.
Notes: Objective: An authenticated HTTPS listener that shares nothing with the KMIP port, and cannot be flooded.

## Slide 10
STEP 3 OF 14 · PROPOSED SOLUTION
HTTP transport, sessions and service accounts
An authenticated HTTPS listener that shares nothing with the KMIP port, and cannot be flooded.
Stage B
WHAT GETS BUILT
kmip_pkcs11/api/ with a small stdlib router on ThreadingHTTPServer — the project has three runtime dependencies and none of them does cryptography, which is a property worth keeping.
Middleware order: authenticate, rate limit, route, translate exceptions into RFC 9457 problem+json.
POST and DELETE /api/v1/session, GET /api/v1/me.
CLOSES 3 GAP-MATRIX FEATURES
API keys / service accounts
Connection and rate limiting
Request bounds and DoS resistance
Estimated size: ~900 lines, ~35 tests.
Notes: Objective: An authenticated HTTPS listener that shares nothing with the KMIP port, and cannot be flooded.

## Slide 11
STEP 3 OF 14 · TEST STRATEGY
HTTP transport, sessions and service accounts
An authenticated HTTPS listener that shares nothing with the KMIP port, and cannot be flooded.
Stage B
WHAT THE TESTS HAVE TO PROVE
Login succeeds and fails correctly; a disabled identity is refused; a deleted identity's live session stops working immediately.
Token revocation takes effect on the next request; absolute and idle expiry; a cookie request without a CSRF token is refused while a bearer request is not.
Rate limiting returns 429 and recovers; the connection cap holds under 200 concurrent connections; the KMIP port is unaffected throughout.
Configuration validation refuses api.enabled without TLS.
Every login, logout, token issue and token revoke is an audit row.
GATE
Two hundred concurrent connections do not exhaust the listener, a revoked token is refused on its next use, and the KMIP port serves normally while the API is under load.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 12
STEP 4 OF 14 · DESIGN IMPACT
Read endpoints
Everything a console displays, with authorization identical to KMIP.
Stage B
WHAT CHANGES IN THE EXISTING DESIGN
Read paths gain an HTTP representation; the KMIP path does not change at all.
The 404-versus-403 decision becomes an API contract every later step must preserve.
THE SHAPE OF THE SOLUTION
GET /keys (paged, filtered, sorted), /keys/{uid}, /keys/{uid}/attributes, /audit, /audit/verify, /approvals, /reports/expiring, /reports/inventory.
404 and 403 are chosen deliberately: an object the caller may not see returns the same answer as one that does not exist, so the API does not become an existence oracle.
Notes: Objective: Everything a console displays, with authorization identical to KMIP.

## Slide 13
STEP 4 OF 14 · PROPOSED SOLUTION
Read endpoints
Everything a console displays, with authorization identical to KMIP.
Stage B
WHAT GETS BUILT
Read-only handlers calling the services from step 1 — no store access from the transport layer, which the guard reflection test enforces.
Closes no gap-matrix feature directly. It exists so that every step after it can be built without re-litigating authorization — and so a later endpoint cannot silently become a path around dual control.
Estimated size: ~700 lines, ~40 tests.
Notes: Objective: Everything a console displays, with authorization identical to KMIP.

## Slide 14
STEP 4 OF 14 · TEST STRATEGY
Read endpoints
Everything a console displays, with authorization identical to KMIP.
Stage B
WHAT THE TESTS HAVE TO PROVE
Authorization parity: for a given identity, GET /keys returns exactly the set KMIP Locate returns. Parametrised over owner, admin, grantee, group member and stranger.
The paging contract from step 2 holds through the HTTP layer.
Audit filters by identity, object, result and time range; the approval queue lists pending requests only.
A read of an object the caller may not see is indistinguishable from a read of one that does not exist.
Every read is audited — 'who exported this key' is a read.
GATE
A read-only console renders key inventory, audit search and the approval queue against real data, and a test proves no write path is reachable through any registered route.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 15
STEP 5 OF 14 · DESIGN IMPACT
Write endpoints, and the governance gaps
Lifecycle and delegation over REST, with governance applying by construction rather than by remembering.
Stage B
WHAT CHANGES IN THE EXISTING DESIGN
Write paths over HTTP, with governance applied through the guard rather than re-implemented beside it.
lifecycle/governance.py extends to key pairs, create_split_key gains a second method, and the service layer gains transactions.
The server acquires a data plane. Until now every caller fetched a key reference and asked the token to act on it; now applications send data and never see a key at all.
THE SHAPE OF THE SOLUTION
POST /keys; POST /keys/{uid}/activate | revoke | rekey; DELETE /keys/{uid}; PUT /keys/{uid}/cryptoperiod; grants, groups and role permissions; POST /approvals/{id}/approve.
A dual-control refusal returns 403 carrying the approval request id and the count outstanding, so the console can render 'awaiting 2 approvals' and link to the queue. That falls out of the existing enforcement.
Three matrix gaps are closed here because they are lifecycle work: asymmetric auto-rotation, Shamir threshold split keys, and batch atomicity via a service-level transaction.
The data plane beside the control plane: POST /keys/{uid}/encrypt | decrypt | sign | mac, and /datakey returning a fresh key both wrapped under the named key and in the clear — the surface applications actually consume, and the primitives already run inside the token.
Notes: Objective: Lifecycle and delegation over REST, with governance applying by construction rather than by remembering.

## Slide 16
STEP 5 OF 14 · PROPOSED SOLUTION
Write endpoints, and the governance gaps
Lifecycle and delegation over REST, with governance applying by construction rather than by remembering.
Stage B
WHAT GETS BUILT
All writes go through the guard. Scheduled rotation extends to key pairs using the existing ReKeyKeyPair handler; CreateSplitKey gains a Shamir method alongside XOR; the service layer wraps a batch in one transaction so a mid-batch failure rolls back.
The crypto endpoints are thin: they translate JSON to the arguments the existing Encrypt, Decrypt, Sign and MAC handlers already take. Re-wrap is decrypt-then-encrypt under the successor key, inside one guarded call so plaintext never leaves the process.
CLOSES 4 GAP-MATRIX FEATURES
Automatic rotation
Split knowledge / M-of-N shares
Bulk and batch operations
Encryption as a service (data-plane API)
Estimated size: ~1,350 lines, ~68 tests.
Notes: Objective: Lifecycle and delegation over REST, with governance applying by construction rather than by remembering.

## Slide 17
STEP 5 OF 14 · TEST STRATEGY
Write endpoints, and the governance gaps
Lifecycle and delegation over REST, with governance applying by construction rather than by remembering.
Stage B
WHAT THE TESTS HAVE TO PROVE
The dual-control assertion from the KMIP wire test, run verbatim against REST: the first Destroy is refused, the key survives, two other identities approve, the retry succeeds, and the approval is spent.
Role allowlists and group grants behave identically over both transports — parametrised over the transport, one test body.
Asymmetric rotation cross-links both new objects to both old ones.
Shamir: any k of n shares reconstruct, any k-1 fail.
A batch whose third item fails leaves the first two unapplied.
Ciphertext from the REST encrypt endpoint decrypts over KMIP and the reverse — one test body, both transports, so the two cannot diverge.
A data key returns a wrapped form that unwraps to the plaintext form; re-wrap to the successor key yields the original plaintext and the old ciphertext no longer decrypts under the new version.
GATE
The KMIP dual-control test and the REST dual-control test share one body and both pass.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 18
STEP 6 OF 14 · DESIGN IMPACT
Administration, OpenAPI, separation of duties
Complete the API surface and split the administrator so no one role can both grant access and use it.
Stage B
WHAT CHANGES IN THE EXISTING DESIGN
The admin role splits in two — the first change to the authorization model since Phase 5, and the first needing a migration for existing deployments.
An OpenAPI document becomes a build artefact CI has to keep in step with the router.
THE SHAPE OF THE SOLUTION
Identity, role and group administration endpoints.
The admin role splits into security-admin (identities, roles, policy) and key-admin (objects, cryptoperiods), so a key administrator cannot grant themselves access to what they administer.
An OpenAPI 3.1 document generated from the router's route table, not hand-written — a hand-written spec drifts within a month.
An interactive explorer served from that document, and client libraries generated from it in CI rather than written by hand, for the same reason: anything maintained separately from the router drifts from it.
Notes: Objective: Complete the API surface and split the administrator so no one role can both grant access and use it.

## Slide 19
STEP 6 OF 14 · PROPOSED SOLUTION
Administration, OpenAPI, separation of duties
Complete the API surface and split the administrator so no one role can both grant access and use it.
Stage B
WHAT GETS BUILT
Migration assigns both new roles to anyone holding admin today, so an upgrade changes nobody's access until an operator splits them.
CLOSES 3 GAP-MATRIX FEATURES
REST / JSON API
Separation of duties
OpenAPI specification and generated clients
Estimated size: ~900 lines, ~50 tests.
Notes: Objective: Complete the API surface and split the administrator so no one role can both grant access and use it.

## Slide 20
STEP 6 OF 14 · TEST STRATEGY
Administration, OpenAPI, separation of duties
Complete the API surface and split the administrator so no one role can both grant access and use it.
Stage B
WHAT THE TESTS HAVE TO PROVE
A key-admin cannot create an identity; a security-admin cannot read key material; neither can escalate to the other.
The generated OpenAPI document validates against the 3.1 schema, and a reflection test asserts every registered route appears in it.
A client generated from the document round-trips a create, read and delete against a live server, so the specification is proved usable and not merely well-formed.
Responses for a sample of endpoints match their declared schemas.
GATE
openapi.json validates, covers every route the router knows about, and the two admin roles are provably disjoint in capability.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 21
STEP 7 OF 14 · DESIGN IMPACT
Web console and self-service
The interface most of the market considers table stakes, and the reason the API exists.
Stage B
WHAT CHANGES IN THE EXISTING DESIGN
A front-end build enters the repository — the first artefact that is neither Python nor documentation tooling.
Content Security Policy and cookie handling become part of the security review surface.
THE SHAPE OF THE SOLUTION
A single-page client of the API. No privileged path: the console can do nothing the API forbids, and holds no credential the API would not accept from curl.
Views: key inventory, key detail, approval queue, audit search, expiry report, identity and role administration.
Self-service: a team member creates and rotates keys within their group's grants, without an administrator.
Notes: Objective: The interface most of the market considers table stakes, and the reason the API exists.

## Slide 22
STEP 7 OF 14 · PROPOSED SOLUTION
Web console and self-service
The interface most of the market considers table stakes, and the reason the API exists.
Stage B
WHAT GETS BUILT
Served by the API listener or a CDN. Strict CSP with no unsafe-inline. Session in an httpOnly cookie, never in localStorage.
CLOSES 2 GAP-MATRIX FEATURES
Web console
Self-service developer portal
Estimated size: ~2,000 lines of front-end, ~30 tests.
Notes: Objective: The interface most of the market considers table stakes, and the reason the API exists.

## Slide 23
STEP 7 OF 14 · TEST STRATEGY
Web console and self-service
The interface most of the market considers table stakes, and the reason the API exists.
Stage B
WHAT THE TESTS HAVE TO PROVE
End-to-end with a headless browser (Playwright is available): log in, list keys, open the approval queue, approve a request, watch a blocked Destroy succeed on retry.
The CSP contains no unsafe-inline and no unsafe-eval.
A route the API forbids to this identity is not reachable from the console by any means, including direct navigation.
GATE
An operator completes a full day of routine work — provisioning, approving, investigating an audit question — without touching the CLI.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 24
STEP 8 OF 14 · DESIGN IMPACT
Enterprise identity and policy
Authenticate against the corporate directory, and express conditions the role model cannot.
Stage C
WHAT CHANGES IN THE EXISTING DESIGN
Identity resolution gains a third path beside password and mTLS certificate.
The guard gains a policy evaluation point — the first change to its order of checks since step 1.
THE SHAPE OF THE SOLUTION
OIDC: validate the ID token (issuer, audience, expiry, signature) and map a claim to a provisioned identity. LDAP/AD bind as an alternative.
The mTLS path already proves the pattern — an external assertion resolved to a provisioned principal, never inventing one.
Attribute-based conditions evaluated in the guard before the allowlist: time window, source network, purpose. The engine may only narrow.
Notes: Objective: Authenticate against the corporate directory, and express conditions the role model cannot.

## Slide 25
STEP 8 OF 14 · PROPOSED SOLUTION
Enterprise identity and policy
Authenticate against the corporate directory, and express conditions the role model cannot.
Stage C
WHAT GETS BUILT
Directory group to role mapping, refreshed on login.
Policies stored in the database, versioned, and every evaluation that denies is audited with the rule that fired.
CLOSES 2 GAP-MATRIX FEATURES
Enterprise IdP — LDAP/AD, SAML, OIDC
Attribute or policy-based access
Estimated size: ~900 lines, ~40 tests.
Notes: Objective: Authenticate against the corporate directory, and express conditions the role model cannot.

## Slide 26
STEP 8 OF 14 · TEST STRATEGY
Enterprise identity and policy
Authenticate against the corporate directory, and express conditions the role model cannot.
Stage C
WHAT THE TESTS HAVE TO PROVE
An expired, wrong-audience, wrong-issuer or unsigned token is refused; a valid token for an unprovisioned subject is refused.
Directory group changes take effect on next login.
A policy denies outside its window and permits inside it.
Property test: for any identity and any policy set, the permitted operation set is a subset of what the role model alone would allow. A policy that widens access is a bug by construction.
GATE
A corporate login yields exactly the roles the directory says, and a policy denial names the rule that fired in the audit log.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 27
STEP 9 OF 14 · DESIGN IMPACT
Audit externalisation, compliance and ceremony
Make the audit trail survive an attacker with file access, and produce the evidence an auditor asks for.
Stage C
WHAT CHANGES IN THE EXISTING DESIGN
The audit log stops being purely local: it gains an outbound path and an external dependency.
Worker 0 takes on a third single-instance responsibility beside the scheduler and the metrics endpoint.
Startup gains a sealed state. Every health check, every deployment script and every operator runbook has to account for a service that is running but not yet open.
THE SHAPE OF THE SOLUTION
A shipper emitting audit rows as syslog/CEF, with a persisted cursor so a restart neither duplicates nor loses entries.
Periodic notarisation of the chain digest to an append-only external endpoint. This is the one thing the local chain cannot do: detect a wholesale, internally consistent rewrite.
Compliance report generators over the audit log and key inventory — PCI DSS key-management evidence, NIST SP 800-57 cryptoperiod evidence.
A key ceremony runbook, and a kmip-admin command producing a signed transcript of what was done, by whom and witnessed by whom — extended to the token PIN itself, split into operator-held shares so the service starts sealed and a quorum opens it. Today one PIN holder is the whole ceremony.
OpenTelemetry spans around every guarded operation and token call. Metrics say a request was slow; a span says which PKCS#11 call it waited on.
Alerting rules over the metrics already exported.
Notes: Objective: Make the audit trail survive an attacker with file access, and produce the evidence an auditor asks for.

## Slide 28
STEP 9 OF 14 · PROPOSED SOLUTION
Audit externalisation, compliance and ceremony
Make the audit trail survive an attacker with file access, and produce the evidence an auditor asks for.
Stage C
WHAT GETS BUILT
The shipper runs in worker 0 alongside the scheduler, with the same single-instance reasoning.
CLOSES 7 GAP-MATRIX FEATURES
Formal key ceremony
External audit anchoring
SIEM integration
Compliance reporting
Alerting
Distributed tracing
Sealed startup with quorum unseal
Estimated size: ~1,350 lines, ~60 tests.
Notes: Objective: Make the audit trail survive an attacker with file access, and produce the evidence an auditor asks for.

## Slide 29
STEP 9 OF 14 · TEST STRATEGY
Audit externalisation, compliance and ceremony
Make the audit trail survive an attacker with file access, and produce the evidence an auditor asks for.
Stage C
WHAT THE TESTS HAVE TO PROVE
The shipper emits every row exactly once across a restart — kill it mid-stream and assert the union at the collector.
CEF output parses with a standard parser.
Anchoring detects tampering the local chain cannot: rewrite the whole log consistently, re-chain it so verify_audit_chain passes, and assert the anchor comparison fails.
Report figures match direct store queries.
A ceremony transcript verifies against its signature and fails after a single byte is changed.
Any k of n unseal shares start the service and any k-1 leave it sealed; a sealed service answers /health and refuses every KMIP and REST operation rather than failing obscurely deep in the shim.
A traced request carries one trace id from the HTTP layer through the guard to the token call, and a sampled-out request costs no spans.
GATE
A rewritten but internally consistent audit log — one that passes local verification — is caught by the external anchor.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 30
STEP 10 OF 14 · DESIGN IMPACT
Storage abstraction and PostgreSQL
Remove the single-writer constraint that blocks everything in stage D.
Stage D
WHAT CHANGES IN THE EXISTING DESIGN
metadata/store.py stops being SQLite and becomes an interface with two implementations — the largest structural change in the plan.
Every SQLite-specific mechanism needs a deliberate equivalent, including the lock that stops the audit chain forking.
THE SHAPE OF THE SOLUTION
Extract a Store interface; SQLite becomes one implementation and PostgreSQL another.
Each SQLite-specific mechanism needs a deliberate equivalent, not a translation: PRAGMA user_version becomes a schema-version table, json_extract becomes JSONB operators, RAISE(ABORT) triggers become PL/pgSQL triggers, and BEGIN IMMEDIATE — which is what keeps the audit chain from forking — becomes an advisory lock or SERIALIZABLE.
Notes: Objective: Remove the single-writer constraint that blocks everything in stage D.

## Slide 31
STEP 10 OF 14 · PROPOSED SOLUTION
Storage abstraction and PostgreSQL
Remove the single-writer constraint that blocks everything in stage D.
Stage D
WHAT GETS BUILT
Both backends ship. SQLite stays the default for single-node deployments; it is a good answer there and removing it would be a regression.
CLOSES 1 GAP-MATRIX FEATURE
Enterprise database backend
Estimated size: ~1,500 lines, ~60 tests. Needs a PostgreSQL instance in CI.
Notes: Objective: Remove the single-writer constraint that blocks everything in stage D.

## Slide 32
STEP 10 OF 14 · TEST STRATEGY
Storage abstraction and PostgreSQL
Remove the single-writer constraint that blocks everything in stage D.
Stage D
WHAT THE TESTS HAVE TO PROVE
The entire existing store suite runs against both backends from one parametrised fixture — not a parallel copy that drifts.
The audit chain survives concurrent writers on PostgreSQL: hammer it from several connections and assert the chain verifies and no sequence number is reused.
Migrations apply identically on both; backup and restore work on both.
A store dump from one backend restores into the other.
GATE
The full suite — 816 tests plus everything added since — passes against PostgreSQL as well as SQLite.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 33
STEP 11 OF 14 · DESIGN IMPACT
High availability, failover and deployment
Survive the loss of a node, a token, or a site.
Stage D
WHAT CHANGES IN THE EXISTING DESIGN
Single-process assumptions become cluster-wide ones: the scheduler needs a leader lock, not a worker index.
pkcs11_shim gains a pool and health checks — the first change to the shim's contract since the capability probe.
THE SHAPE OF THE SOLUTION
Several nodes against one PostgreSQL. The scheduler takes a leader lock so exactly one instance enforces cryptoperiods — the same reasoning that restricts it to worker 0 today, one level up.
An HSM pool: several tokens, health-checked, with failover. The master key must exist on each, which makes provisioning part of the design rather than an afterthought.
Scheduled backup with offsite shipping; Helm chart and manifests; the container image and CI workflow finally executed.
Notes: Objective: Survive the loss of a node, a token, or a site.

## Slide 34
STEP 11 OF 14 · PROPOSED SOLUTION
High availability, failover and deployment
Survive the loss of a node, a token, or a site.
Stage D
WHAT GETS BUILT
Read traffic spreads across nodes; audited writes still serialise on the chain, so this raises availability more than throughput. Say so rather than implying linear scaling.
CLOSES 6 GAP-MATRIX FEATURES
HA clustering
Multi-site replication and DR
HSM failover and pooling
Horizontal throughput
Scheduled and offsite backup
Kubernetes / container deployment
Estimated size: ~1,800 lines, ~55 tests. Needs multiple nodes and a second token.
Notes: Objective: Survive the loss of a node, a token, or a site.

## Slide 35
STEP 11 OF 14 · TEST STRATEGY
High availability, failover and deployment
Survive the loss of a node, a token, or a site.
Stage D
WHAT THE TESTS HAVE TO PROVE
Kill the leader under load: another takes over within the lease period, and no key is deactivated twice.
Fail a token mid-operation: the request either completes on another or fails cleanly, never silently half-applies.
Two nodes serving concurrently produce one intact audit chain.
A scheduled backup taken on one node restores on another.
The container image builds and its health check passes — the first time this has been executed anywhere.
GATE
A node is killed under sustained load: no request is lost, the audit chain verifies, and cryptoperiod enforcement continues uninterrupted.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 36
STEP 12 OF 14 · DESIGN IMPACT
Multi-tenancy
Let unrelated tenants share one deployment without seeing each other.
Stage D
WHAT CHANGES IN THE EXISTING DESIGN
A tenant column reaches every table, every query, the audit log, the CLI and the API.
Object names stop being globally unique — the change most likely to surprise an existing deployment.
THE SHAPE OF THE SOLUTION
Tenant becomes a first-class column on objects, identities and audit rows, and every query is scoped by it.
Object names become unique per tenant rather than globally — the change most likely to surprise an existing deployment.
Quotas: object count, operations per second, storage. Per-tenant audit views. Tenant administrators who cannot see other tenants.
This is why it is last: the boundary reaches into every query, the audit log, the CLI and the API, and half of it would be worse than none.
Notes: Objective: Let unrelated tenants share one deployment without seeing each other.

## Slide 37
STEP 12 OF 14 · PROPOSED SOLUTION
Multi-tenancy
Let unrelated tenants share one deployment without seeing each other.
Stage D
WHAT GETS BUILT
A migration places every existing object in a default tenant, so a single-tenant deployment behaves exactly as before.
CLOSES 2 GAP-MATRIX FEATURES
Multi-tenancy and namespaces
Per-tenant quotas
Estimated size: ~1,600 lines, ~80 tests.
Notes: Objective: Let unrelated tenants share one deployment without seeing each other.

## Slide 38
STEP 12 OF 14 · TEST STRATEGY
Multi-tenancy
Let unrelated tenants share one deployment without seeing each other.
Stage D
WHAT THE TESTS HAVE TO PROVE
Exhaustive isolation: parametrised over all 41 KMIP operations and every REST route, an identity in tenant B cannot read, modify, locate or destroy an object in tenant A. This is the test that matters and it should be generated from the operation table, not hand-written.
Name collisions across tenants are allowed; within a tenant they are not.
Quota enforcement at the boundary, and the audit row that records it.
A tenant administrator cannot escalate out of their tenant.
Audit search returns only the caller's tenant.
GATE
A generated test over every operation and every route proves no cross-tenant reachability exists.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 39
STEP 13 OF 14 · DESIGN IMPACT
KMIP JSON and XML encodings
Let a client speak KMIP without implementing a TTLV codec.
Stage E
WHAT CHANGES IN THE EXISTING DESIGN
core/ttlv.py stops being the only codec, and the tag registry becomes shared infrastructure rather than a TTLV detail.
Nothing above the codec changes. That is the point of the step: the service layer cannot tell which encoding a request arrived in.
THE SHAPE OF THE SOLUTION
The object model does not change. What changes is the wire: a JSON codec and an XML one beside core/ttlv.py, both driven by the same tag and type tables, so a new tag is still added in one place.
An HTTPS binding on the API listener — POST /kmip, encoding chosen by Content-Type — rather than a second socket. The KMIP TCP port is untouched.
Encoding is a transport concern, so it sits below the service layer: the same guard, the same handlers, the same audit rows.
Notes: Objective: Let a client speak KMIP without implementing a TTLV codec.

## Slide 40
STEP 13 OF 14 · PROPOSED SOLUTION
KMIP JSON and XML encodings
Let a client speak KMIP without implementing a TTLV codec.
Stage E
WHAT GETS BUILT
core/encodings/ with json.py and xml.py implementing the OASIS profiles, sharing the tag registry the TTLV codec already reads.
Content negotiation, and 415 for an encoding that is not enabled. Both are off by default: a new parser is new attack surface.
CLOSES 1 GAP-MATRIX FEATURE
KMIP JSON and XML encodings
Estimated size: ~700 lines, ~40 tests — mostly the existing corpus re-parametrised.
Notes: Objective: Let a client speak KMIP without implementing a TTLV codec.

## Slide 41
STEP 13 OF 14 · TEST STRATEGY
KMIP JSON and XML encodings
Let a client speak KMIP without implementing a TTLV codec.
Stage E
WHAT THE TESTS HAVE TO PROVE
Round-trip every operation's request and response through all three encodings and assert the decoded structures are identical — the existing conformance corpus re-run twice, not a new set of assertions.
The OASIS JSON and XML test vectors decode to what the TTLV vectors decode to.
A batch, a wrapped key and a dual-control refusal behave the same over JSON as over TTLV, so an encoding cannot change semantics.
An unknown tag, a truncated document and a type mismatch are refused with the same error the TTLV codec raises.
GATE
The conformance suite passes unchanged when re-run against the JSON and XML encodings, and a request refused over TTLV is refused identically over both.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 42
STEP 14 OF 14 · DESIGN IMPACT
Certificate discovery and expiry monitoring
Know which certificates the estate is actually running, and warn before one expires.
Stage E
WHAT CHANGES IN THE EXISTING DESIGN
The server starts reaching outward. Everything else here waits to be called; this initiates connections, which is a new posture for the service and for its firewall rules.
The inventory stops being a view of what this KMS holds and becomes a view of the estate, including certificates it does not manage.
THE SHAPE OF THE SOLUTION
A scanner that connects to configured TLS endpoints, records the chain presented, and stores subject, issuer, fingerprint and validity window against the inventory.
Certificates registered here are matched by fingerprint, so the report separates what this KMS manages from what it does not — the second number is the one that matters.
Expiry thresholds feed the alerting rules built in step 9 rather than opening a second notification path.
Notes: Objective: Know which certificates the estate is actually running, and warn before one expires.

## Slide 43
STEP 14 OF 14 · PROPOSED SOLUTION
Certificate discovery and expiry monitoring
Know which certificates the estate is actually running, and warn before one expires.
Stage E
WHAT GETS BUILT
kmip_pkcs11/discovery/ with the scanner, a scheduler entry beside the cryptoperiod scheduler in worker 0, and the inventory tables.
Scanning is read-only and rate-limited. This is a tool that touches production endpoints, and it should be incapable of harming them.
CLOSES 1 GAP-MATRIX FEATURE
Certificate discovery and expiry monitoring
Estimated size: ~600 lines, ~30 tests.
Notes: Objective: Know which certificates the estate is actually running, and warn before one expires.

## Slide 44
STEP 14 OF 14 · TEST STRATEGY
Certificate discovery and expiry monitoring
Know which certificates the estate is actually running, and warn before one expires.
Stage E
WHAT THE TESTS HAVE TO PROVE
A scan of local TLS servers with known certificates records exactly those chains, intermediate included.
A certificate registered here and the same certificate found by scanning reconcile to one inventory row, matched on fingerprint.
An endpoint that times out, presents an expired certificate, or drops the handshake is recorded as such rather than skipped silently.
An expiry threshold fires once per certificate per window, not on every scan.
GATE
A scan of a fixture estate reports every certificate, splits managed from unmanaged correctly, and raises an expiry alert exactly once for a certificate inside the warning window.
Notes: A step is finished when its gate is demonstrated, not when its code is written. Tests run live against a real SoftHSM2 token — the token is never mocked, because the defects worth catching are at that boundary.

## Slide 45
AFTER STEP 12
What the plan does not close
INTEGRATION
Cloud BYOK (AWS, Azure, GCP) · Cloud EKM / XKS / hold-your-own-key
VALIDATION
Database TDE integration · Storage, backup and VM integrations
PRODUCT SCOPE
Secrets management · Certificate lifecycle
SUPPLIER
Algorithm breadth · Post-quantum (ML-KEM, ML-DSA, SLH-DSA) · Key-bound usage policy enforced in hardware
OPTIONAL STEP
KMIP 3.0
EXTERNAL
KMIP interoperability certification
DEMAND
PKCS#11 provider for applications
OUT OF SCOPE
Tokenization / format-preserving encryption
PROCUREMENT
FIPS 140-2/3 validated HSM · Common Criteria / eIDAS
34 of 50 closed by the 14 steps. 8 more are work someone could schedule — integration, vendor validation, or a product decision. The last 8 depend on a supplier, a procurement decision, an OASIS event or hardware this project cannot verify; no amount of planning moves them.
Notes: Close on the honest boundary: the plan says what it cannot do as clearly as what it can, and the generator refuses to build if those two lists stop adding up to the gap matrix.